## Table_of_Contents_Tracking
Section Number | Section Name | Details | Level | Requirement Status | Development Status | Assigned To | Priority | Notes | Last Updated | Remark
1 | Abbreviations and Acronyms |  | 1 | NOT STARTED |  |  |  |  | 2025-01-27
2 | LMS Architecture Diagram |  | 1 | NOT STARTED |  |  |  |  | 2025-01-27
3 | External Interface Requirements |  | 1 | NOT STARTED |  |  |  |  | 2025-01-27
4 | Role and User Management |  | 1 | IN REVIEW |  |  |  |  | 2025-01-27
4.1 | List of Roles |  | 2 | [5 empty] | 2025-01-27
4.2 | Authorization Matrix by Feature |  | 2 | [5 empty] | 2025-01-27
4.3 | User Management |  | 2 | [5 empty] | 2025-01-27
4.3.1 | User Creation Screen |  | 3 | [5 empty] | 2025-01-27
4.3.2 | User Listing Page |  | 3 | [5 empty] | 2025-01-27
4.3.3 | Login Authentication |  | 3 | [5 empty] | 2025-01-27
4.4 | Role & Permission Management |  | 2 | [5 empty] | 2025-01-27
4.4.1 | Permission Categories and Definitions |  | 3 | [5 empty] | 2025-01-27
4.4.2 | Default Role Permission Matrix |  | 3 | [5 empty] | 2025-01-27
4.4.3 | Role & Permission Management Screen |  | 3 | [5 empty] | 2025-01-27
4.4.4 | Edit Permissions Modal |  | 3 | [5 empty] | 2025-01-27
4.4.5 | Permission Management Business Rules |  | 3 | [5 empty] | 2025-01-27
4.4.8 | Integration with Other Features |  | 3 | [5 empty] | 2025-01-27
4.5 | Role-Based Data Filtering |  | 2 | [5 empty] | 2025-01-27
4.5.1 | Data Filtering Rules by Role |  | 3 | [5 empty] | 2025-01-27
4.5.2 | Dashboard Statistics Filtering |  | 3 | [5 empty] | 2025-01-27
4.5.3 | Course List Filtering |  | 3 | [5 empty] | 2025-01-27
4.5.4 | Pending Approvals Filtering |  | 3 | [5 empty] | 2025-01-27
4.5.5 | Approval Workflow Integration |  | 3 | [5 empty] | 2025-01-27
5 | Trainer Management |  | 1 | IN PROGRESS |  |  |  |  | 2025-01-27
5.1 | Trainer Creation Page |  | 2 | [5 empty] | 2025-01-27
5.2 | Trainer Listing Page |  | 2 | [5 empty] | 2025-01-27
5.3 | Trainer Details Page |  | 2 | [5 empty] | 2025-01-27
6 | Participant Management |  | 1 | IN PROGRESS |  |  |  |  | 2025-01-27
6.1 | Integration |  | 2 | IN PROGRESS |  |  |  |  | 2025-01-27
6.2 | Participant List |  | 2 | IN PROGRESS |  |  |  |  | 2025-01-27
6.3 | Participant Details Page |  | 2 | IN PROGRESS |  |  |  |  | 2025-01-27
7 | Content Management |  | 1 | IN REVIEW |  |  |  |  | 2025-01-27
7.1 | Modules |  | 2 | [5 empty] | 2025-01-27
7.1.1 | Module Data Structure |  | 3 | [5 empty] | 2025-01-27
7.1.2 | Module Listing Page |  | 3 | [5 empty] | 2025-01-27
7.1.3 | Module Creation Form |  | 3 | [5 empty] | 2025-01-27
7.1.4 | Module Details Page |  | 3 | [5 empty] | 2025-01-27
7.1.5 | Module Status Management |  | 3 | [5 empty] | 2025-01-27
7.1.6 | Module Clone Functionality |  | 3 | [5 empty] | 2025-01-27
7.1.7 | Module Delete Functionality |  | 3 | [5 empty] | 2025-01-27
7.1.8 | Module Integration Points |  | 3 | [5 empty] | 2025-01-27
7.1.9 | Module Authorization Matrix |  | 3 | [5 empty] | 2025-01-27
7.1.10 | Module Validation Rules |  | 3 | [5 empty] | 2025-01-27
7.2 | Product |  | 2 | [5 empty] | 2025-01-27
7.2.1 | Product Data Structure |  | 3 | [5 empty] | 2025-01-27
7.2.2 | Product Listing Page |  | 3 | [5 empty] | 2025-01-27
7.2.3 | Product Details Page |  | 3 | [5 empty] | 2025-01-27
7.2.4 | Product Creation |  | 3 | [5 empty] | 2025-01-27
7.2.5 | Product Status Management |  | 3 | [5 empty] | 2025-01-27
7.2.6 | Product Clone Functionality |  | 3 | [5 empty] | 2025-01-27
7.2.7 | Product Delete Functionality |  | 3 | [5 empty] | 2025-01-27
7.2.8 | Product Integration Points |  | 3 | [5 empty] | 2025-01-27
7.2.9 | Product Authorization Matrix |  | 3 | [5 empty] | 2025-01-27
7.2.10 | Product Validation Rules |  | 3 | [5 empty] | 2025-01-27
7.3 | Program |  | 2 | [5 empty] | 2025-01-27
7.3.1 | Program Data Structure |  | 3 | [5 empty] | 2025-01-27
7.3.2 | Program Management Features |  | 3 | [5 empty] | 2025-01-27
7.3.3 | Program Status Management |  | 3 | [5 empty] | 2025-01-27
7.3.4 | Program Integration Points |  | 3 | [5 empty] | 2025-01-27
7.3.5 | Future Enhancements |  | 3 | [5 empty] | 2025-01-27
8 | Course Management |  | 1 | IN REVIEW |  |  |  |  | 2025-01-27
8.1 | Course Creation |  | 2 | [5 empty] | 2025-01-27
8.1.1 | Course Creation Form |  | 3 | [5 empty] | 2025-01-27
8.1.1.1 | Dynamic Form Behavior Based on Course Type |  | 4 | [5 empty] | 2025-01-27
8.1.1.2 | SHINE Form Fields |  | 4 | [5 empty] | 2025-01-27
8.1.1.3 | Product Form Fields |  | 4 | [5 empty] | 2025-01-27
8.1.1.4 | Skill Form Fields |  | 4 | [5 empty] | 2025-01-27
8.1.1.5 | Course Code Generation Logic |  | 4 | [5 empty] | 2025-01-27
8.1.1.6 | Status Transition Logic |  | 4 | [5 empty] | 2025-01-27
8.1.1.7 | Checklist Template Application |  | 4 | [5 empty] | 2025-01-27
8.1.1.8 | Co-trainer Management |  | 4 | [5 empty] | 2025-01-27
8.1.2 | Entry Points |  | 3 | [5 empty] | 2025-01-27
8.1.3 | Validation & Error Handling |  | 3 | [5 empty] | 2025-01-27
8.2 | Course Listing Screen |  | 2 |  | X |  |  |  | 2025-01-27
8.2.1 | Course List View | - Show course list grid with Sorting Ability - Support collumn configuration | 3 |  | X |  |  |  | 2025-01-27
8.2.2 | Filter & Search | - Course Filter and Search | 3 |  | X |  |  |  | 2025-01-27
8.2.3 | Export Courses | - Course Export to CSV template | 3 |  | O |  |  |  | 2025-01-27
8.3 | Course Details Screen |  | 2 | [5 empty] | 2025-01-27
8.3.1 | Course General Tab | - Show course basic information - Show course AOL information - Show course MOF information (SHINE) | 3 |  | X |  |  |  | 2025-01-27
8.3.1.1 | Course Status Timeline | - Show course status timeline with details information about state change | 4 |  | X |  |  |  | 2025-01-27
8.3.1.2 | Course Approval Actions |  | 4 | [5 empty] | 2025-01-27
8.3.2 | Course History | - Show course update history | 3 |  | O |  |  |  | 2025-01-27
8.3.3 | Course Planning Tab | - Show course stages with details such as Trainer, Start&End date etc - Enable Planning Update for authorised user - Resource Allocation Alert (Trainer Unavailable alert) | 3 |  | X |  |  |  | 2025-01-27
8.3.4 | Course Participant Tab | - Show course participant list with details - Show the applicable course actions | 3 |  | X |  |  |  | 2025-01-27
8.4 | Course Registration |  | 2 | [5 empty] | 2025-01-27
8.4.1 | Registration Process |  | 3 | [5 empty] | 2025-01-27
8.4.2 | Registration Approval Workflow | - Approval Determination - Send approval request email/notification (template setup in Survey) - Approve/Reject - Course Status Update - Mail/notification on the approval result | 3 | [5 empty] | 2025-01-27
8.4.3 | Auto-Cancellation Rule |  | 3 | [5 empty] | 2025-01-27
8.5 | Course Edit |  | 2 | [5 empty] | 2025-01-27
8.5.1 | Edit Authorization Matrix | - Determine if user is authorised for course edit to display the edit option | 3 | [5 empty] | 2025-01-27
8.5.2 | Edit Approval Workflow | - Approval Determination - Send approval request email/notification (template setup in Survey) - Approve/Reject - Course Status Update - Mail/notification on the approval result | 3 | [5 empty] | 2025-01-27
8.5.3 | Field-Level Restrictions |  | 3 | [5 empty] | 2025-01-27
8.6 | Course Cancel |  | 2 | [5 empty] | 2025-01-27
8.6.1 | Cancel Authorization Matrix | - Determine if course can be canceled - Determine if user is authorised for course cancel to display the edit option | 3 | [5 empty] | 2025-01-27
8.6.2 | Cancel Approval Workflow | - Approval Determination - Send approval request email/notification (template setup in Survey) - Approve/Reject - Course Status Update - Mail/notification on the approval result | 3 | [5 empty] | 2025-01-27
8.6.3 | Direct Cancellation (No Approval) | - Support direct cancellation for authorised user | 3 | [5 empty] | 2025-01-27
8.6.4 | Business Rules |  | 3 | [5 empty] | 2025-01-27
8.7 | Course Delete |  | 2 | [5 empty] | 2025-01-27
8.7.1 | Delete Authorization Matrix | - Enabled edit option to authorised user for deletable course | 3 | [5 empty] | 2025-01-27
8.7.2 | Delete Workflow | - Update course status - Email, Notification | 3 | [5 empty] | 2025-01-27
8.8 | Course Operations |  | 2 | [5 empty] | 2025-01-27
8.8.1 | Course Participant List |  | 3 | [5 empty] | 2025-01-27
8.8.2 | Add Participant to Course with Import File | - Allow add participant to course with import file - Participant Details Validation - Participant Duplication Check - Support add re-exam participant to course - Implement Specific import participant logic check by course channel, type etc | 3 | [5 empty] | 2025-01-27
8.8.3 | Add Participant to Course Manually | - Enable UI for add existing participant to course for re-exam - Show list of participants that are applicable to be added to course - Participant Search and Filter during adding participant to course | 3 | [5 empty] | 2025-01-27
8.8.4 | Export Participants | - Export Participant List to CSV file base on the current applied filtering | 3 | [5 empty] | 2025-01-27
8.8.5 | Export Participants for MOF Exam | - Determine the Participants that are eligible for MOF exam - Export Participant to CSV predefined templete for MOF exam | 3 | [5 empty] | 2025-01-27
8.8.6 | Import MOF Exam Result | - Allow Import MOF Exam Result with import file - Match the participant by id - Update the participant MOF result - Import file error handling - Import file outcome returning to user | 3 | [5 empty] | 2025-01-27
8.8.7 | Confirm Passed Participant | - Show button allow authorised user to confirm passed participant - Send email passed participant confirmed (templete setup in Survey) | 3 | [5 empty] | 2025-01-27
8.8.8 | Export Passed Participant | - Determine Passed Participants - Export Passed Participants to Predefined CSV file | 3 | [5 empty] | 2025-01-27
8.8.9 | Attendance Check | - API post attendance check - Display the attenhance check result for each participant in course | 3 | [5 empty] | 2025-01-27
8.8.10 | AOL Exam Result | - Support API post AOL exam Result - Display the AOL exam result to course participant | 3 | [5 empty] | 2025-01-27
8.8.11 | Configurable Final Result Calculation Rules | - Enable final result calculation logic customization - Auto calculate the final result based on the configured logic | 3 | [5 empty] | 2025-01-27
8.8.12 | Manually Set Passed/Failed | - Enable the ability to manually set the final result to passed/failed - Allow manually overide the calculated result | 3 | [5 empty] | 2025-01-27
8.8.13 |  | - Support API for granting the Agent Code - Store the Agent Code by Participant | 3 | [5 empty] | 2025-01-27
8.9 | Course Type Checklist Configuration |  | 2 | [5 empty] | 2025-01-27
8.9.1 | Course Checklist by Course Type Definition |  | 3 | [5 empty] | 2025-01-27
8.9.2 | Email and Notification |  | 3 | [5 empty] | 2025-01-27
8.9.2.1 | Checklist Notification |  | 4 | [5 empty] | 2025-01-27
8.9.2.2 | Checklist Notification Templates |  | 4 | [5 empty] | 2025-01-27
8.9.3 | Show Course Checklist in Course Details |  | 3 | [5 empty] | 2025-01-27
8.9.3.1 | Course Checklist Details and Actions |  | 4 | [5 empty] | 2025-01-27
8.9.3.2 | Business Rules |  | 4 | [5 empty] | 2025-01-27
8.9.4 | Authorization Matrix |  | 3 | [5 empty] | 2025-01-27
8.9.5 | Course MOF addresses registration and participant allocation |  | 3 | [5 empty] | 2025-01-27
8.1 | Course Import Function [PHASE 2] |  | 2 | PHASE 2 | [5 empty] | 2025-01-27
9 | PIC Calendar |  | 1 | IN PROGRESS |  |  |  |  | 2025-01-27
9.1 | View Courses Per Trainer |  | 2 | [5 empty] | 2025-01-27
9.1.1 | Matrix Calendar Layout |  | 3 | [5 empty] | 2025-01-27
9.1.2 | Course Display in Calendar Cells |  | 3 | [5 empty] | 2025-01-27
9.1.3 | Trainer Display Customization |  | 3 | [5 empty] | 2025-01-27
9.1.4 | Filter Options |  | 3 | [5 empty] | 2025-01-27
9.1.5 | Role-Based Authorization |  | 3 | [5 empty] | 2025-01-27
9.1.6 | Trainer Workload Tooltip |  | 3 | [5 empty] | 2025-01-27
9.1.7 | Interactive Features |  | 3 | [5 empty] | 2025-01-27
9.1.8 | Month Navigation |  | 3 | [5 empty] | 2025-01-27
9.1.9 | Empty State Handling |  | 3 | [5 empty] | 2025-01-27
9.1.10 | Default Screen After Login |  | 3 | [5 empty] | 2025-01-27
9.2 | View Trainer Assignment for Each Trainer |  | 2 | [5 empty] | 2025-01-27
9.3 | Export PIC Calendar Data |  | 2 | [5 empty] | 2025-01-27
10 | Master Calendar |  | 1 | IN PROGRESS |  |  |  |  | 2025-01-27
10.1 | View Courses in Master Calendar |  | 2 | [5 empty] | 2025-01-27
10.1.1 | Matrix Calendar Layout |  | 3 | [5 empty] | 2025-01-27
10.1.2 | Course Display in Calendar Cells |  | 3 | [5 empty] | 2025-01-27
10.1.3 | Program Display Customization |  | 3 | [5 empty] | 2025-01-27
10.1.4 | Filter Options |  | 3 | [5 empty] | 2025-01-27
10.1.5 | Month Navigation |  | 3 | [5 empty] | 2025-01-27
10.1.6 | Interactive Features |  | 3 | [5 empty] | 2025-01-27
10.1.7 | Empty State Handling |  | 3 | [5 empty] | 2025-01-27
10.1.9 | Performance Optimization |  | 3 | [5 empty] | 2025-01-27
10.1.11 | Program-Based Course Creation |  | 3 | [5 empty] | 2025-01-27
10.2 | Create Course in Master Calendar |  | 2 | [5 empty] | 2025-01-27
10.3 | Other Actions in Master Calendar |  | 2 | [5 empty] | 2025-01-27
10.3.1 | Course Registration |  | 3 | [5 empty] | 2025-01-27
10.3.2 | Course Edit |  | 3 | [5 empty] | 2025-01-27
10.3.3 | Course Delete |  | 3 | [5 empty] | 2025-01-27
10.3.4 | View Details |  | 3 | [5 empty] | 2025-01-27
10.3.5 | Export Course |  | 3 | [5 empty] | 2025-01-27
11 | List Manage |  | 1 | IN PROGRESS |  |  |  |  | 2025-01-27
12 | Configuration Module
12.1 | Course Configuration |  | 2 | READY
12.1.1 | Course Type Checklist Configuration |  | 3 | READY
12.1.1.1 | Course Checklist by Course Type Definition | - Different checklist per course types for SHINE, PRODUCT, SKILL | 4 | READY
12.1.1.2 | Show Course Checklist in Course Details | - Show course checklist, PIC and completion status for each task | 4 | READY
12.1.2 | Date Rule Configuration |  | 3 | READY
12.2 | Holiday Calendar Configuration |  | 2 | READY
12.2.1 | Holiday Registration |  | 3 | READY
12.2.2 | Holiday Skip During Course Planning |  | 3 | READY
12.2.3 | Holiday Display in PIC Calendar |  | 3 | READY
12.3 | Email and Notification |  | 2 | [6 empty] | Feature has been built in Survey
12.3.1 | Default Email and Notification Template |  | 3
12.3.2 | Email and Notification Custimization |  | 3
13 | Report Management [PHASE 2] |  | 1 | NOT STARTED |  |  |  |  | 2025-01-27
13.1 | SHINE PASS RATIO |  | 2 | [5 empty] | 2025-01-27
13.2 | SHINE TRAINING |  | 2 | [5 empty] | 2025-01-27
13.3 | PARTICIPANT OF TRAINERS |  | 2 | [5 empty] | 2025-01-27
13.4 | RECRUITMENT SHINE |  | 2 | [5 empty] | 2025-01-27
13.5 | DANH SACH DANG KY MOF |  | 2 | [5 empty] | 2025-01-27
13.6 | PASS RATIO BY MONTH |  | 2 | [5 empty] | 2025-01-27
13.7 | GIO BAY TRAINER |  | 2 | [5 empty] | 2025-01-27
13.8 | ATTENDANCE REPORT |  | 2 | [5 empty] | 2025-01-27
13.9 | REPORT FOR FWD AGENT TRAINING ACTIVITY |  | 2 | [5 empty] | 2025-01-27
13.1 | SHINE REPORT |  | 2 | [5 empty] | 2025-01-27
13.11 | FWT TRAINER PAYSLIP |  | 2 | [5 empty] | 2025-01-27
13.12 | EXAM FEE TOTAL |  | 2 | [5 empty] | 2025-01-27
14 | General Setting |  | 1 | [5 empty] | 2025-01-27
14.1 | SMTP Settings |  | 2 | [5 empty] | 2025-01-27